## Sheet1
PRODUCT BACKLOG TEMPLATE
Javascript Project Sort Books 1.1
ID | As a | I want to be able to | So that | Priority | Sprint (est. Hours) | Status
#General | Programmer | write a pseudocode version of the project | i can sort the code and keep it organized so that its easier to read and built | 1 |  | 100%
#General | Programmer | sort and read the syntax comments as easy as possible | i dont have to read every line to understand the code | 1 |  | 100%
#FilterBooks | User | filter the genres | so that i can easily find books in the right genre for me | 2 |  | 100%
#addBook | Admin | Add a book with Author, Title, Genre and cover | i can keep the libary up to date and wont loose my data in the libary | 3 |  | 80%
#addBook | Admin | get a warning when not adding author and title and genre to book | i can't add a book without key information | 1 |  | 100%
#SortBooks | User | Sort the books according to title and author | i don't have to look at a random order | 2 |  | 100%
#bookList | Admin | Keep my array of added books in localstorage | when i refresh my browser, i can still see the books ive added | 3 |  | 100%
#searchBook | User | Search for a book and be given suggestions during my typing in the searchfield | i dont have to type the complete word before finding the decired book | 4 |  | 0%
#editBooks | Admin | edit the information given to the book added | i can change the values of input e.g. incase of misspelling | 4 |  | 0%
#deleteBooks | Admin | delete a book from the libary | users cant find this book if the libary doesnt have it anymore | 4 |  | 0%
Note on G7: Need to be able to add the cover image selected by user, as background-image of bookPic div
spørgsmål til optimering:
- Hvordan kan man ellers opdele sit script så det er lettere at finde frem til funktioner, uden brug af /******/ for at vise hvad der kommer herfra og ned? ville det være lettere at læse og smartere hvis man evt. opdelte scripts filer? e.g. anvende en scriptfil til localstorage, og en til addbook, osv.?
- addBooks checkIfnfoLegit() og dets if statements , kunne det være undgået "required" på hvert html element i stedet for if statements?
- console log when localstorage is cleared = hvor skal console.warn(sessionStorage.getItem("consoleWarnAfterReload")); kaldes henne, for at være i console efter reload og ikke før? skal den lille bid loades før resten af scriptet loades?
- generel optimering af syntax hvor jeg gentager mig selv, eks. sort books med deres compare funktioner, hvordan kunne de skrives smartere?
MANGLER:
- tilføj billede til cover på bog ud fra input fil
- søg efter bog info og få forslag for hver karakter der skrives i søgefeltet
- slet en bog fra arrayet
- ændre info i en bog